## Application Roadmap
VERNALIS ENTERPRISE ATTENDANCE & PAYROLL SYSTEM — APPLICATION CREATION ROADMAP
Comprehensive chronological steps, architecture decisions, database models, RBAC security, and statutory payroll engine ¦ Generated: September 2026
Phase # | Step / Milestone ID | Milestone Title | Workstream / Category | Key Technical Implementation Details | Deliverables & Key Files | Verification & Testing Method | Status
Phase 1 | STEP-01 | Project Architecture & Foundation Scaffold | Foundation & Tooling | Initialized Next.js 16 (App Router) with React 19, TypeScript 5.7, Tailwind CSS v4, Lucide icons, and modern module path aliasing (@/*). Established responsive grid layouts and dark/light color schemes. | package.json, tsconfig.json, app/layout.tsx, app/globals.css | npm run build & compilation validation | Completed
Phase 1 | STEP-02 | Domain Entity Modeling & TypeScript Contracts | Data Architecture | Authored strongly typed interfaces for Employee, AttendanceRecord, CorrectionRequest, LeaveRequest, LeaveBalance, and Role (employee, manager, hr, payroll). Defined immutable status enums. | lib/types.ts, lib/mock-data.ts | npx tsc --noEmit strict type checking | Completed
Phase 2 | STEP-03 | Interactive Attendance Marking & Clock Engine | Frontend & Logic | Engineered real-time Punch-In / Punch-Out clock widget with elapsed hour timer, GPS location mock/capture, IP address tracking, automated shift tagging, and auto-determination of late arrival status (>09:15 AM). | components/attendance/views/employee-view.tsx, components/attendance/clock-widget.tsx | Interactive UI punch tests across shifts | Completed
Phase 2 | STEP-04 | Muster Roll & Monthly Attendance Matrix | Frontend & Reporting | Built calendar grid rendering monthly presence (Present, Half-Day, Late Mark, WFH, Absent, On-Leave). Implemented multi-filter timesheet with search, date range picking, and Excel/CSV data export. | components/attendance/views/employee-view.tsx, lib/mock-data.ts | Visual audit across 31 days calendar edge cases | Completed
Phase 2 | STEP-05 | Attendance Regularization / Correction Workflow | Workflow & Forms | Implemented modal form allowing employees to submit attendance corrections with reasons (Forgot to punch, biometric failure, client visit) and proposed clock-in/out timestamps. | components/attendance/store.tsx, app/api/corrections/route.ts | Form validation & correction creation check | Completed
Phase 2 | STEP-06 | Statutory Leave Application & Quota Management | HR Management | Created leave application drawer tracking Casual Leave (CL), Sick Leave (SL), and Earned Leave (EL) quotas. Built balance decrement logic and visual quota health indicators. | components/attendance/store.tsx, app/api/leaves/route.ts | Leave balance math check on submit | Completed
Phase 3 | STEP-07 | Statutory Payroll Calculation Engine & Indian Labor Rules | Payroll Engine | Formulated statutory payroll rules: (1) 3 late marks = 0.5 day Loss of Pay (LOP) penalty; (2) Half-day = 0.5 payable day; (3) Approved paid leave = 1.0 payable day; (4) Non-negative clamping of payable days. | lib/server/attendance-db.ts, test/payroll-math.test.ts | Automated test suite (11 unit tests) | Verified
Phase 3 | STEP-08 | Statutory Payroll Math Automated Test Suite | Testing & QA | Configured Node.js native test runner (node --test --experimental-strip-types) executing 11 isolated unit test suites verifying base pay, late mark tiers, unpaid leaves, and multi-factor scenarios. | test/payroll-math.test.ts, package.json (npm test) | npm test (11/11 tests pass with 0 failures) | Verified
Phase 3 | STEP-09 | Server-Side Period Locking & Payroll Summary API | Backend & Finance | Built /api/payroll endpoint computing dynamic salary registers and an immutable period lock mechanism (POST /api/payroll { locked: true }) to prevent retro-active attendance tampering. | app/api/payroll/route.ts, components/attendance/views/payroll-view.tsx | E2E API test for period lock & unlock | Completed
Phase 4 | STEP-10 | Four Dedicated Role Workspaces & Tab Gating | Frontend UI/UX | Constructed isolated dashboards: (1) Employee Portal; (2) Manager Portal with team muster & approvals; (3) HR Admin Command with directory & muster register; (4) Payroll Officer Workspace with salary math. | components/attendance/role-workspace.tsx, components/attendance/portal-shell.tsx | Multi-role responsive UI rendering tests | Completed
Phase 4 | STEP-11 | Mobile & Tablet Responsive Polish | Frontend UI/UX | Ensured tables, action bars, and navigation tabs feature horizontal overflow scrolling (overflow-x-auto, min-w-[650px]) and touch-friendly controls across small viewport screens (<380px). | components/attendance/views/payroll-view.tsx, components/attendance/views/hr-view.tsx | Viewport emulation on mobile and tablet devices | Completed
Phase 5 | STEP-12 | Supabase Cloud PostgreSQL Architecture & Schema DDL | Database Cloud | Designed 6 normalized relational tables: employees, attendance_records, correction_requests, leave_requests, leave_balances, and payroll_locks with foreign keys, cascades, and composite indexes. | supabase/schema.sql | SQL DDL execution in Supabase Cloud SQL Editor | Completed
Phase 5 | STEP-13 | Supabase Client & Bidirectional Snake/Camel Mappers | Database Integration | Integrated @supabase/supabase-js with type-safe schema interfaces. Implemented data transformation mappers bridging PostgreSQL snake_case columns with frontend camelCase domain models. | lib/supabase.ts | Type validation & mock schema mapping tests | Completed
Phase 5 | STEP-14 | Zero-Downtime Server Database Repository with Fallback | Resilience Architecture | Implemented asynchronous CRUD in lib/server/attendance-db.ts with automatic failover to in-memory store if cloud credentials are absent or remote queries fail, guaranteeing 100% build uptime. | lib/server/attendance-db.ts | Dual-mode test with and without Supabase keys | Completed
Phase 5 | STEP-15 | Enterprise Cloud Data Seeding & Synchronization | Data Migration | Migrated 10 enterprise employees, default leave quotas (12 CL, 10 SL, 15 EL), and 472 attendance records for August 2026 into Supabase Cloud project (https://nesfzgaamvppdcwvdnee.supabase.co). | scratch/seed-supabase.mjs, portal-shell.tsx status badge | Live Supabase table query verification | Verified
Phase 6 | STEP-16 | NextAuth v4 Authentication with JWT Session Cookies | Security & Auth | Configured NextAuth with Credentials Provider, signed JWT session cookies, custom session callbacks, and environment secrets (NEXTAUTH_SECRET, NEXTAUTH_URL). Removed client-side role dropdown. | lib/auth.ts, app/api/auth/[...nextauth]/route.ts, .env.local | NextAuth login token generation & decoding | Completed
Phase 6 | STEP-17 | Edge Middleware Route Interception & Access Gating | Edge Security | Deployed Next.js Edge Middleware (middleware.ts) intercepting all /portal/* routes. Unauthenticated requests are redirected to /login; unauthorized roles are sent to /portal/unauthorized. | middleware.ts, app/portal/unauthorized/page.tsx | Edge route interception tests across all roles | Completed
Phase 6 | STEP-18 | Server-Side API Least-Privilege Data Scoping | Backend Security | Hardened all API endpoints (/api/bootstrap, /api/attendance, /api/corrections, /api/leaves). Employees only see their own records. Salaries are redacted to 0 for non-HR/Payroll callers. | lib/server/auth.ts, app/api/bootstrap/route.ts | Automated security penetration test suite (21 tests) | Verified
Phase 6 | STEP-19 | Modern Sign-In Portal with 1-Click Role Demonstrators | Frontend UI/UX | Built dedicated login interface (/login) with email/password authentication, demo credentials, and 1-click role switcher cards for Sadiya (Emp), Vikram (Mgr), Meera (HR), and Sanjay (Payroll). | app/login/page.tsx | Manual & automated sign-in flows | Completed
Phase 7 | STEP-20 | Public Employee Registration Portal | Onboarding & Auth | Engineered registration interface at /register with fields for Full Name, Work Email, Password, Requested Role, Department, Designation, and Reporting Manager selection. | app/register/page.tsx, app/api/register/route.ts | Form submission & validation checks | Completed
Phase 7 | STEP-21 | Candidate Pending Review State Lifecycle | State Machine | Configured new registrations to start in status: "pending". NextAuth credentials check blocks unapproved candidates from logging in with a clear notice directing them to contact HR/Manager. | lib/auth.ts, app/login/page.tsx | Attempted login before approval yields explicit alert | Verified
Phase 7 | STEP-22 | HR & Manager Approval Queue Component | Admin Workspaces | Built RegistrationsView component added to HR (/portal/hr) and Manager (/portal/manager) workspaces. Features tab filters (Pending, All, Approved, Rejected) and live count badges. | components/attendance/views/registrations-view.tsx, components/attendance/role-workspace.tsx | Live badge counter & tab switching audit | Completed
Phase 7 | STEP-23 | Atomic Employee Provisioning & Activation Engine | Backend & DB | Implemented approveRegistrationRequest: inserts approved candidate into Supabase employees table, credits 12 CL, 10 SL, 15 EL in leave_balances, generates initial calendar, and unlocks credentials. | lib/server/attendance-db.ts, app/api/registrations/[id]/route.ts | End-to-end registration -> approval -> login test | Verified
Phase 7 | STEP-24 | Rejection Lifecycle & Audit Logging | Governance | Implemented rejectRegistrationRequest marking candidate status as "rejected", recording reviewer ID and timestamp, preventing unauthorized sign-ins. | lib/server/attendance-db.ts, app/api/registrations/[id]/route.ts | Rejection endpoint testing & UI status update | Completed
Phase 8 | STEP-25 | Production Build Compilation & Type Invariance Audit | Compilation & CI | Ran npx tsc --noEmit (0 errors) and npm run build. Successfully generated 20 optimized App Router static and dynamic route handlers with Edge middleware bundle. | All project files | npm run build (0 warnings, 0 errors) | Verified
Phase 8 | STEP-26 | Version Control & Git Remote Synchronization | DevOps & Git | Cleanly staged and committed all features with atomic semantic messages. Pushed branch to GitHub repository (https://github.com/SADIYA2002/Vernalis-Project.git on origin/main). | git origin/main branch | git push origin main verification | Completed
Phase 8 | STEP-27 | Vercel Cloud Deployment & Environment Variables Guide | Deployment | Documented Vercel deployment requirements: configured NEXTAUTH_SECRET, NEXTAUTH_URL, NEXT_PUBLIC_SUPABASE_URL, NEXT_PUBLIC_SUPABASE_PUBLISHABLE_KEY, and SUPABASE_SERVICE_ROLE_KEY. | walkthrough.md, Vercel Project Settings | Vercel deployment readiness check | Completed
Phase 8 | STEP-28 | Documentation, Testing Walkthrough & Excel Roadmap Delivery | Documentation | Generated comprehensive walkthrough.md artifact, implementation plan, and formatted Excel workbook detailing the entire technical journey and verification logs. | walkthrough.md, Vernalis_Attendance_Payroll_Application_Roadmap.xlsx | Excel workbook validation & structure audit | Completed

## Role-Based Access Matrix
VERNALIS ATTENDANCE & PAYROLL — ROLE-BASED ACCESS CONTROL (RBAC) MATRIX
Security boundary, Edge route interception, and least-privilege API authorization policy
Feature / Resource | Endpoint / Route | Employee Role | Manager Role | HR Admin Role | Payroll Officer Role | Security Enforcement Layer
Employee Portal Workspace | /portal/employee | Full Access (Self) | Full Access (Self) | Full Access (Self) | Full Access (Self) | Edge Middleware + Server Layout
Manager Team Workspace | /portal/manager | Access Denied (403) | Full Access (Direct Reports) | Full Access (All Teams) | Access Denied (403) | Edge Middleware + Server Component
HR Central Admin Workspace | /portal/hr | Access Denied (403) | Access Denied (403) | Full Access (Company Wide) | Access Denied (403) | Edge Middleware + Server Component
Payroll Processing Workspace | /portal/payroll | Access Denied (403) | Access Denied (403) | Full Access (Read/Write) | Full Access (Compute & Lock) | Edge Middleware + Server Component
Attendance Clock In/Out API | POST /api/attendance | Allowed (Own ID Only) | Allowed (Own ID Only) | Allowed (Own ID Only) | Allowed (Own ID Only) | Server Session Identity Check
Correction Request Review API | POST /api/corrections/[id] | Access Denied (403) | Allowed (Direct Reports Only) | Allowed (All Employees) | Access Denied (403) | Direct Report Verification in DB
Leave Application Review API | POST /api/leaves/[id] | Access Denied (403) | Allowed (Direct Reports Only) | Allowed (All Employees) | Access Denied (403) | Direct Report Verification in DB
Candidate Registration Approval | POST /api/registrations/[id] | Access Denied (403) | Allowed (Assigned Team Joinees) | Allowed (All Joinees) | Access Denied (403) | Manager Assignment Check + HR Override
Payroll Computation & Salary Exposure | GET /api/payroll | Salary Redacted (0) / 403 | Salary Redacted (0) / 403 | Unredacted Salaries | Unredacted Salaries | Least-Privilege Scoping in API
Payroll Cycle Period Lock | POST /api/payroll | Access Denied (403) | Access Denied (403) | Allowed (Lock & Unlock) | Allowed (Lock & Unlock) | Role Guard requireAuth(["payroll","hr"])

## Statutory Payroll Rules
STATUTORY PAYROLL CALCULATION ENGINE & POLICY SPECIFICATION
Indian Labor Law statutory attendance rules, late arrival penalization tiers, and automated unit test suite
Rule ID | Policy Name | Policy Rule & Business Logic | Mathematical Formulation | Test Scenario in test/payroll-math.test.ts | Validation Status
RULE-01 | Full Attendance & Base Salary | Employee attending all scheduled working days receives 100% of agreed monthly salary with zero deduction. | Payable Days = Total Working Days; Net Salary = Monthly Salary | Rule 1: Full Attendance & Base Computation | 100% PASS
RULE-02 | Late Arrival Grace Window | Employees arriving past 09:15 AM receive late mark. 1 or 2 late marks in a monthly cycle are treated as grace period with 0 penalty. | If lateCount < 3 => lateDeductionDays = 0.0 | Rule 2: Late Arrival Penalty (applies no salary deduction for 1-2 marks) | 100% PASS
RULE-03 | Late Arrival Penalty Tier (3-Mark Rule) | Every cumulative tier of 3 late marks incurs exactly 0.5 day Loss of Pay (LOP) deduction from payable days. | lateDeductionDays = Math.floor(lateCount / 3) * 0.5 | Rule 2: deducts 0.5 day for 3 lates; 1.0 day for 6 lates | 100% PASS
RULE-04 | Half-Day Attendance | A half-day shift (morning or afternoon half) credits 0.5 payable day and incurs 0.5 day Loss of Pay (LOP). | Half-Day Payable = 0.5; Half-Day LOP = 0.5 | Rule 3: Half-Day Attendance | 100% PASS
RULE-05 | Unexcused Absence (LOP) | Unexcused absence results in a full 1.0 day Loss of Pay deduction from payable days. | LOP Days += 1.0; Payable Days -= 1.0 | Rule 4: Absence & Loss of Pay | 100% PASS
RULE-06 | Approved Paid Leave Quota | Approved Casual Leave (CL), Sick Leave (SL), and Earned Leave (EL) count as fully paid days. | Paid Leave Days = 1.0 payable; LOP = 0.0 | Rule 5: Paid Leave vs Leave Without Pay | 100% PASS
RULE-07 | Leave Without Pay (LWP) | Leave taken beyond allotted quota or unpaid leaves incur full 1.0 day Loss of Pay deduction. | LWP Days = 1.0 LOP; Payable Days -= 1.0 | Rule 5: Approved LWP deducts payable day | 100% PASS
RULE-08 | Boundary Clamping to Zero | Under extreme absenteeism, total payable days cannot fall below zero (no negative salary balances). | Payable Days = Math.max(0, Working Days - Total Deductions) | Rule 7: Boundary Conditions & Non-Negative Clamping | 100% PASS
RULE-09 | Prorated Net Attendance Salary | Gross salary is strictly prorated against verified payable days over the total working days in the payroll cycle. | Net Pay = Math.round((Payable Days / Working Days) * Monthly Salary) | Rule 6: Complex Multi-Factor Payroll Simulation | 100% PASS

## Database Schema (PostgreSQL)
SUPABASE CLOUD POSTGRESQL DATA ARCHITECTURE
Normalized relational tables, foreign key constraints, indexes, and cloud synchronization mapping
Table Name | Column Name | Data Type & Constraints | Foreign Key & References | Description & Business Purpose
employees | id | TEXT PRIMARY KEY | None | Unique employee ID (e.g. emp-01, mgr-01)
employees | name | TEXT NOT NULL | None | Full legal name
employees | email | TEXT UNIQUE NOT NULL | None | Corporate email address for login
employees | role | TEXT NOT NULL | None | Role enum: employee, manager, hr, payroll
employees | department | TEXT NOT NULL | None | Department (Engineering, Product, HR, Finance)
employees | designation | TEXT NOT NULL | None | Official job designation
employees | manager_id | TEXT | employees(id) | Self-referencing foreign key to reporting manager
employees | monthly_salary | NUMERIC DEFAULT 0 | None | Base gross monthly salary (redacted for non-HR)
attendance_records | id | TEXT PRIMARY KEY | None | Unique record identifier
attendance_records | employee_id | TEXT NOT NULL | employees(id) ON DELETE CASCADE | Associated employee
attendance_records | date | DATE NOT NULL | None | Attendance calendar date (YYYY-MM-DD)
attendance_records | status | TEXT NOT NULL | None | present, late, half_day, wfh, absent, on_leave
attendance_records | clock_in / clock_out | TEXT | None | Actual recorded timestamps (HH:MM)
attendance_records | worked_hours | NUMERIC DEFAULT 0 | None | Computed daily work hours
leave_balances | employee_id | TEXT PRIMARY KEY | employees(id) ON DELETE CASCADE | Associated employee
leave_balances | casual | NUMERIC DEFAULT 12 | None | Casual Leave balance remaining
leave_balances | sick | NUMERIC DEFAULT 10 | None | Sick Leave balance remaining
leave_balances | earned | NUMERIC DEFAULT 15 | None | Earned / Privilege Leave balance remaining
correction_requests | id | TEXT PRIMARY KEY | None | Unique request identifier
correction_requests | employee_id | TEXT NOT NULL | employees(id) | Submitting employee
correction_requests | status | TEXT DEFAULT "pending" | None | pending, approved, rejected
correction_requests | reviewer_id | TEXT | employees(id) | Manager or HR who approved/rejected
leave_requests | id | TEXT PRIMARY KEY | None | Unique leave request identifier
leave_requests | employee_id | TEXT NOT NULL | employees(id) | Submitting employee
leave_requests | leave_type | TEXT NOT NULL | None | casual, sick, earned, unpaid
leave_requests | status | TEXT DEFAULT "pending" | None | pending, approved, rejected
registration_requests | id | TEXT PRIMARY KEY | None | Unique registration request identifier
registration_requests | name / email | TEXT NOT NULL | None | Candidate credentials & identity
registration_requests | status | TEXT DEFAULT "pending" | None | pending, approved, rejected
registration_requests | manager_id | TEXT | employees(id) | Assigned reporting manager for approval
payroll_locks | period_key | TEXT PRIMARY KEY | None | Payroll period (e.g. 2026-08)
payroll_locks | is_locked | BOOLEAN DEFAULT FALSE | None | Freeze attendance modifications
payroll_locks | locked_by | TEXT | employees(id) | Payroll officer who committed cycle lock